## Responsibility Traceability Mat
Item ID | Deliverable | Associated Requiement | Requirement Orgin | Responsibility person
1 | Project Requrement / Deliverable
1.1 | Project Charter | Project Kick off/ Defining High level project structure including scope,requirment,exclusion etc | Shared | Project Director
1.2 | Project Requirement
1.2.1 | Requirement Management plan | All Project Requirements will be captured and traceable to how those requirements will be satisfied through the project cycle. | Shared | Project Manager
1.3 | Budget
1.3.1 | Cost Performance Baseline | A Baseline will exist to monitor and control project expnditure through the project lifecycle | Pioneer Pvt | Project Finance officer
1.3.2 | Cost Management plan | The plans and processess that pioneer pvt ltd will use to monitor and control project expenditure through the project lifecycle will be clearly defined | Sugahspice | Project Finance officer
1.4 | Schedule
1.4.1 | Schedule baseline | A Baseline will exist to monitor and control the achievement of project milestones and progress through the project lifecycle. | Pioneer Pvt | Project Manager
1.4.2 | Schedule management plan | The plans and processess that pioneer pvt ltd will use to monitor and control project milestones and progress through the project lifecycle will be clearly defined | Sugahspice | Project Manager
1.5 | Resource
1.5.1 | Responsibility charts/Assignment | Project Leadership,Structure and responsibility followed by Pioneer pvt ltd will be clearly defineed and available at a glance. | Sugahspice | Project Manager
1.5.2 | Human Resource plan | The plans and processess that Pioneer Pvt Ltd will use to appoint the members of the project team will be clearly defined. | Sugahspice | Project Manager
1.5.3 | Communication Management plan | The plans and processess that Pioneer Pvt Ltd will use to communicate the project progress and issues both internal as well as external will be clearly defined. | Sugahspice | Project Manager
1.6 | Scope
1.6.1 | Scope Statement | A Summary of the scope the Pioneer Intends to deliver through the project lifecysle will be clearly defined. | Sugahspice | Project Manager
1.6.2 | WBS | Each work package of the scope used to faciliate the execution of the project by Pioneer Pvt Ltd will be clearly defined and available at a glance. | Sugahspice | Project Manager
1.6.3 | Scope Baseline | A baseline will exist to monitor and control scope through the project lifecycle. | Pioneer Pvt | Project Manager
1.6.4 | Scope Management Plan | The plans and processes that Pioneer Pvt Ltd will be use to monitor and control the scope through the project life cycle will be clearly defined. | Sugahspice | Project Manager
1.7 | Risk Assessment
1.7.1 | Risk Management plan | The plans and Processess that Pioneer Pvt Ltd will use to monitor and control all risks assosiated with the project will be clearly defined. | Sugahspice | Project Manager
1.8 | Other Management plans and Reports
| Process improvement plan | The plans and process that Pioneer Pvt Ltd will used to improve its internal plans and process through the project life cycle will be clearly defined. | Sugahspice | Project Manager
| Quality Management Plan | The plans and processess that Pioneer Pvt Ltd will use to ensure the quality of all the applicable deliverables through the project lifecycle will be clearly defined. | Sugahspice | Project Manager
| Procurement Management Plan | The plans and processess that Pioneer Pvt Ltd will use to ensure the procurement of all the applicable deliverables through the project lifecycle will be clearly defined. | Sugahspice | Project Manager
| Weekly Progress Report | Pioneer Pvt Ltd will track the project's Performance against all applicable baselined through the project lifecycle and provide regular updates to the stakeholders. | Sugahspice | Project Manager
| Project Completion Summary Report | Pioneer Pvt Ltd will summarize the results and success of the project immediately following the execution of the event in order to faciliate project close out. | Sugahspice | Project Manager
1.9 | Product Requirement /Deliverable
1.9.1 | Material Procurement | All the material required for the proeject will be handled by the procurement team which includes creation of RFI,PO,Contracts,material delivery and handling. | Sugahspice | Project Manager
1.9.2 | License and service certification | The service related licence if necessary will ensure that all the required licence for the concern department are obtained as per the regulations. | Sugahspice | Project Manager